DODDL

Website Migration Plan & Complete Task List

Phase 1: New Site Architecture · Phase 2: International Migration

| Prepared for | Doddl Ltd — Jon Fawcett |
| --- | --- |
| Prepared by | Claude — SEO & GEO Specialist |
| Date | 2025 |
| Version | 1.0 — Final for PM handoff |

# Executive Summary

This document covers the complete migration plan for the Doddl website — a major evolution from a two-section product store to a developmental journey-led architecture across three international markets.

The project is structured in two phases. Phase 1 delivers the new site architecture, new page builds, technical SEO fixes, and US market activation. Phase 2 migrates the German market from doddlbaby.de to doddl.com/de/ as a separate, sequenced workstream to manage risk.

| Phase 1 Duration | Phase 2 Duration | New Pages to Build | Issues Resolved |
| --- | --- | --- | --- |
| 6–8 weeks | 4–6 weeks post-launch | 18 pages | 14 issues |

## Locked Decisions

All items below are confirmed and not subject to further debate. The migration plan is built on these foundations.

| Decision | Outcome |
| --- | --- |
| Store structure | Single Shopify store, standard plan, Shopify Markets |
| Market URL structure | doddl.com (UK) · doddl.com/en-us/ (US) · doddl.com/de/ (DE, Phase 2) |
| DE brand domain | doddlbaby.de → migrates to doddl.com/de/ in Phase 2, then decommissioned |
| Content rule | English for UK + US · German for DE via Translate & Adapt |
| Market-specific images | Translate & Adapt for media per market (Option B) |
| URL pattern | Keyword + stage number + age range (e.g. /collections/baby-cutlery-stage-1-6-12-months) |
| SEN journey URLs | /pages/sen-feeding-journey-[milestone] pattern |
| Mealtime Dev Box URLs | /pages/mealtime-development-box-stage-[n]-[age] pattern |
| Blog tag clusters | Shopify blog tags for stage-aligned article clusters |
| Geo-blocking | Addify only — BoostMark to be uninstalled |
| Analytics | Native Shopify GA4 only · GTM revisit as separate workstream |

# Phase Overview

| Phase | Name | Duration | Key Output |
| --- | --- | --- | --- |
| 0 | Immediate actions & admin | 1–2 days | Clean, stable starting point |
| 1A | Pre-duplication setup | 3–5 days | Theme pulled, audited, ready to duplicate |
| 1B | Theme build — new pages | 3–4 weeks | 18 new pages built and content-ready |
| 1C | International fixes & redirects | 1 week | hreflang fixed, US activated, redirects live |
| 1D | QA & pre-launch | 1 week | All pages verified across all markets |
| 1E | Go-live & monitoring | Ongoing | Site published, monitoring active |
| 2 | doddlbaby.de migration | 4–6 weeks after launch | DE fully on doddl.com/de/ |

# Phase 0 — Immediate Actions

These tasks have no dependencies. They should be done now, before anything else, regardless of where the wider project is. Total estimated time: 1–2 hours.

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Uninstall BoostMark (BM Country Blocker) from Shopify Admin → Apps | Human | Shopify Admin | 5 mins | 🔥 High |
| Remove French and Spanish from Admin → Settings → Languages | Human | Shopify Admin | 5 mins | 🔥 High |
| Verify site:shop.doddl.com in Google — confirm no indexed pages | Human | Google Search | 10 mins | ⚡ Medium |
| Review Google Ads connection — Admin → Sales Channels → Google & YouTube | Human | Shopify Admin | 15 mins | ⚡ Medium |
| Create dedicated US catalog in USD — Admin → Markets → Catalogs | Human | Shopify Admin | 30 mins | 🔥 High |
| Assign new USD catalog to United States market — remove from Eurozone 1 | Human | Shopify Admin | 15 mins | 🔥 High |
| Remove doddl.com/de as a serving domain for Germany market — Admin → Markets → Germany → Domains | Human | Shopify Admin | 15 mins | 🔥 High |

# Phase 1A — Pre-Duplication Setup

Everything that must be done on the live theme before duplication. This phase ensures the duplicated theme starts from a clean, audited baseline.

## Theme Pull & Audit

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Install Shopify CLI — npm install -g @shopify/cli @shopify/theme | Human | Terminal | 15 mins | 🔥 High |
| Pull live theme — shopify theme pull --store=doddl-ltd.myshopify.com | Human | Shopify CLI | 15 mins | 🔥 High |
| Audit Section Store pages — identify every page using Section Store sections before duplication | Human | Shopify Admin | 2 hrs | 🔥 High |
| Document all Section Store sections in use with page names and section types | Human | Manual | 1 hr | 🔥 High |
| Run full template/section/layout audit on pulled theme files | Claude Code | Claude Code | 1 hr | 🔥 High |
| Screenshot all key page templates as visual baseline for regression testing | Claude Code | Claude Code | 1 hr | ⚡ Medium |
| Run CWV benchmark on live site — record LCP, CLS, INP per key template | Claude Code | Claude Code + PSI | 1 hr | ⚡ Medium |
| Extract and document all current schema markup across key page types | Claude Code | Claude Code | 1 hr | ⚡ Medium |
| Crawl live hreflang and canonical tags — document current state as baseline | Claude Code | Claude Code | 30 mins | 🔥 High |

## Pre-Duplication Redirects

These four category URL changes must be set up as Shopify redirects BEFORE the new URLs go live. Import the redirect CSV built during the planning phase.

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Import pre-launch redirect CSV — Admin → Online Store → Navigation → URL Redirects → Import | Human | Shopify Admin | 15 mins | 🔥 High |
| Verify all 7 pre-launch redirects are working — spot check each one | Claude Code | Claude Code | 30 mins | 🔥 High |

# Phase 1B — Theme Build: New Pages

Duplicate the current live theme. All build work happens in the duplicate — the live site is never touched until go-live.

Duplication: Shopify Admin → Online Store → Themes → (current theme) → ··· → Duplicate.

## New Collections — Shop by Stage

Five entirely new collection pages. No equivalent exists on the current site. These are the structural centrepiece of the new architecture.

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Create Shopify collection: weaning-stage-0-6-months | Human | Shopify Admin | 15 mins | 🔥 High |
| Create Shopify collection: baby-cutlery-stage-1-6-12-months | Human | Shopify Admin | 15 mins | 🔥 High |
| Create Shopify collection: toddler-cutlery-stage-2-12-18-months | Human | Shopify Admin | 15 mins | 🔥 High |
| Create Shopify collection: toddler-cutlery-stage-3-18-months-3-years | Human | Shopify Admin | 15 mins | 🔥 High |
| Create Shopify collection: toddler-cutlery-stage-4-3-5-years | Human | Shopify Admin | 15 mins | 🔥 High |
| Assign correct products to each stage collection | Human | Shopify Admin | 2 hrs | 🔥 High |
| Build stage collection template in Liquid — developmental journey layout with age indicator, product grid, internal links to adjacent stages | Claude Code | Claude Code | 1 day | 🔥 High |
| Add Product schema + CollectionPage schema to stage collection template | Claude Code | Claude Code | 2 hrs | 🔥 High |
| Write English copy for all 5 stage collection pages (H1, intro, SEO description) | Human | Manual | 1 day | 🔥 High |
| Add German translations for all 5 stage collection pages in Translate & Adapt | Human | Translate & Adapt | 1 day | 🔥 High |
| Assign market-specific product images per stage collection in Translate & Adapt | Human | Translate & Adapt | 1 day | ⚡ Medium |
| Verify stage collections render correctly at /en-us/ market URL | Claude Code | Claude Code | 1 hr | 🔥 High |

## New Collections — Shop by Category (Renamed + New)

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Rename collection handle: discover-baby-cutlery → baby-cutlery (Shopify Admin) | Human | Shopify Admin | 10 mins | 🔥 High |
| Rename collection handle: discover-toddler-cutlery → toddler-cutlery | Human | Shopify Admin | 10 mins | 🔥 High |
| Rename collection handle: discover-plates-bowls → plates-and-bowls | Human | Shopify Admin | 10 mins | 🔥 High |
| Rename collection handle: gifting → bundles-and-kits | Human | Shopify Admin | 10 mins | 🔥 High |
| Create new Bibs collection — /collections/bibs — assign bib products | Human | Shopify Admin | 30 mins | 🔥 High |
| Redirect /collections/infant-cutlery-6-month → /collections/baby-cutlery (already in CSV) | Human | Shopify Admin | In CSV | 🔥 High |
| Update navigation in theme to use new collection handles | Claude Code | Claude Code | 1 hr | 🔥 High |

## New Pages — SEN Feeding Journey

One existing page evolves into the hub. Four new pages are built beneath it.

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Create new page: /pages/sen-feeding-journey (hub) | Human | Shopify Admin | 10 mins | 🔥 High |
| Create new page: /pages/sen-feeding-journey-just-starting-out | Human | Shopify Admin | 10 mins | 🔥 High |
| Create new page: /pages/sen-feeding-journey-finding-their-grip | Human | Shopify Admin | 10 mins | 🔥 High |
| Create new page: /pages/sen-feeding-journey-building-confidence | Human | Shopify Admin | 10 mins | 🔥 High |
| Create new page: /pages/sen-feeding-journey-eating-independently | Human | Shopify Admin | 10 mins | 🔥 High |
| Build SEN journey Liquid template — milestone-based layout, product recommendations, internal navigation | Claude Code | Claude Code | 1 day | 🔥 High |
| Add 301 redirect: /pages/doddl-is-for-every-child → /pages/sen-feeding-journey | Human | Shopify Admin | 5 mins | 🔥 High |
| Add FAQPage schema + Article schema to SEN hub page | Claude Code | Claude Code | 1 hr | ⚡ Medium |
| Write English copy for all 5 SEN pages | Human | Manual | 1.5 days | 🔥 High |
| Add German translations for all 5 SEN pages in Translate & Adapt | Human | Translate & Adapt | 1 day | 🔥 High |

## New Pages — Mealtime Development Box

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Create new page: /pages/mealtime-development-box (hub) | Human | Shopify Admin | 10 mins | 🔥 High |
| Create new page: /pages/mealtime-development-box-stage-1-6-12-months | Human | Shopify Admin | 10 mins | 🔥 High |
| Create new page: /pages/mealtime-development-box-stage-2-12-18-months | Human | Shopify Admin | 10 mins | 🔥 High |
| Create new page: /pages/mealtime-development-box-stage-3-18-months-3-years | Human | Shopify Admin | 10 mins | 🔥 High |
| Create new page: /pages/mealtime-development-box-stage-4-3-5-years | Human | Shopify Admin | 10 mins | 🔥 High |
| Add 301 redirect: /pages/complete-baby-to-toddler-mealtime-set → /pages/mealtime-development-box | Human | Shopify Admin | 5 mins | 🔥 High |
| Build Mealtime Development Box Liquid template — box contents, stage progression, bundle CTA | Claude Code | Claude Code | 1 day | 🔥 High |
| Add Product/Offer/ItemList schema to MDB stage pages | Claude Code | Claude Code | 1 hr | ⚡ Medium |
| Write English copy for all 5 MDB pages | Human | Manual | 1.5 days | 🔥 High |
| Add German translations for all 5 MDB pages in Translate & Adapt | Human | Translate & Adapt | 1 day | 🔥 High |

## New Pages — Research & Development

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Create new page: /pages/research-and-development (hub) | Human | Shopify Admin | 10 mins | ⚡ Medium |
| Build Research hub Liquid template — methodology, evidence, expert citations | Claude Code | Claude Code | 4 hrs | ⚡ Medium |
| Add Article + Organization schema to Research hub | Claude Code | Claude Code | 1 hr | ⚡ Medium |
| Write English copy for Research hub | Human | Manual | 4 hrs | ⚡ Medium |
| Add German translation for Research hub in Translate & Adapt | Human | Translate & Adapt | 3 hrs | ⚡ Medium |

## Tips & Advice — Blog Tag Clusters

No URL changes. Tags are applied to existing articles in Shopify Admin → Blog posts. This creates the stage-aligned cluster navigation.

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Apply tag "stage-0-1" to all 16 weaning and introducing solids articles | Human | Shopify Admin | 2 hrs | ⚡ Medium |
| Apply tag "stage-1-2" to all 13 motor skills and cutlery articles | Human | Shopify Admin | 1.5 hrs | ⚡ Medium |
| Apply tag "stage-2-4" to all 20 fussy eating and independence articles | Human | Shopify Admin | 2 hrs | ⚡ Medium |
| Apply tag "general" to all remaining general tips articles (57+) | Human | Shopify Admin | 3 hrs | 📌 Low |
| Build blog tag template in Liquid — cluster landing page with article grid and stage context | Claude Code | Claude Code | 4 hrs | ⚡ Medium |

## Page Cleanup

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Delete page /pages/new_about_us and verify 301 → /pages/about is working | Human | Shopify Admin | 10 mins | 🔥 High |
| Delete page /pages/avada-faqs and verify 301 → /pages/faqs is working | Human | Shopify Admin | 10 mins | 🔥 High |
| Add noindex meta tag to /pages/survey via Liquid theme edit | Claude Code | Claude Code | 30 mins | ⚡ Medium |

# Phase 1C — International Architecture Fixes

These changes fix the international routing, hreflang, and US market visibility. They must be completed before go-live.

## US Market Activation

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Verify US USD catalog is correctly configured (Phase 0 prerequisite) | Human | Shopify Admin | Pre-req | 🔥 High |
| Activate /en-us/ URL prefix — Admin → Markets → United States → Domains → URL prefix: en-us | Human | Shopify Admin | 15 mins | 🔥 High |
| Verify US pages are accessible at doddl.com/en-us/ after activation | Claude Code | Claude Code | 30 mins | 🔥 High |
| Confirm Addify geo-routing is not blocking Googlebot from /en-us/ URLs | Human + Claude Code | Claude Code | 30 mins | 🔥 High |

## Hreflang Fix — Phase 1

Edit layout/theme.liquid (or wherever hreflang is generated). Applies to the duplicated theme before go-live.

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Locate hreflang generation in theme Liquid — identify file and line numbers | Claude Code | Claude Code | 30 mins | 🔥 High |
| Change "en" locale code to "en-GB" for UK market | Claude Code | Claude Code | 30 mins | 🔥 High |
| Add "en-US" hreflang tag pointing to doddl.com/en-us/[page] | Claude Code | Claude Code | 30 mins | 🔥 High |
| Remove generic "de" hreflang entry pointing to doddl.com/de | Claude Code | Claude Code | 15 mins | 🔥 High |
| Fix "de-DE" hreflang target from doddlbaby.de/de → doddlbaby.de/ (root, no subfolder) | Claude Code | Claude Code | 15 mins | 🔥 High |
| Remove "en-DE" hreflang entry — not a valid locale for this architecture | Claude Code | Claude Code | 15 mins | 🔥 High |
| Validate final hreflang cluster on homepage and product page using Rich Results Test | Claude Code | Claude Code | 30 mins | 🔥 High |

# Phase 1D — App QA & Pre-Launch Checks

Complete all app block verification and run the full QA suite before publishing. Nothing goes live until every item in this section is checked.

## App Block Verification

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Reinstall and reconfigure Section Store sections on any pages that used them | Human | Shopify Theme Editor | 2–4 hrs | 🔥 High |
| Verify Opinew review widgets render correctly on PDP template in duplicated theme | Human | Theme Preview | 30 mins | ⚡ Medium |
| Identify all pages using Tolstoy video embeds — verify app blocks are intact | Human | Theme Preview | 30 mins | ⚡ Medium |
| Verify Octane AI quiz renders on correct pages — assess if quiz should appear on new stage pages | Human | Theme Preview | 30 mins | ⚡ Medium |
| Verify Klarna On-Site Messaging renders on PDP and cart templates | Human | Theme Preview | 20 mins | ⚡ Medium |
| Verify Essential Upsell renders on PDP template | Human | Theme Preview | 20 mins | ⚡ Medium |
| Verify Klaviyo email capture forms render on all new page templates | Human | Theme Preview | 45 mins | ⚡ Medium |

## Technical QA Checklist

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Full crawl of duplicated theme in preview — check for 404s, redirect errors, missing pages | Claude Code | Claude Code | 2 hrs | 🔥 High |
| Verify all 18 new pages are accessible and rendering correctly | Claude Code | Claude Code | 1 hr | 🔥 High |
| Verify all 301 redirects from the redirect map are working correctly | Claude Code | Claude Code | 1 hr | 🔥 High |
| Check canonical tags on all new page types — must be self-referential | Claude Code | Claude Code | 1 hr | 🔥 High |
| Validate hreflang across homepage, product page, collection, blog article | Claude Code | Claude Code | 1 hr | 🔥 High |
| Validate schema markup on all new page types using Rich Results Test | Claude Code | Claude Code | 2 hrs | 🔥 High |
| Run CWV benchmark on new theme — compare LCP/CLS/INP vs baseline captured in Phase 1A | Claude Code | Claude Code + PSI | 1 hr | ⚡ Medium |
| Cross-market render test — view all new pages as UK, US, and DE market | Human | Theme Preview | 1 hr | 🔥 High |
| Verify German translations appear correctly on doddlbaby.de preview | Human | Theme Preview | 45 mins | 🔥 High |
| Verify USD pricing appears correctly on /en-us/ pages | Human | Theme Preview | 30 mins | 🔥 High |
| Verify market-specific product images are rendering per market via Translate & Adapt | Human | Theme Preview | 45 mins | ⚡ Medium |
| Check robots.txt — confirm no new page types are accidentally blocked | Claude Code | Claude Code | 15 mins | 🔥 High |
| Check XML sitemap — confirm new pages will be included post-publish | Claude Code | Claude Code | 30 mins | 🔥 High |
| Navigation QA — verify all new sections appear correctly in main nav and footer | Human | Theme Preview | 30 mins | 🔥 High |
| Mobile QA — check all new page templates on mobile viewport | Human | Theme Preview | 1 hr | ⚡ Medium |

# Phase 1E — Go-Live & Post-Launch Monitoring

## Go-Live Sequence

Follow this sequence exactly. Do not deviate from the order.

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Final pre-publish sign-off — all QA checks passed, all stakeholders confirmed | Human | Manual | 30 mins | 🔥 High |
| Publish duplicated theme — Shopify Admin → Online Store → Themes → Publish | Human | Shopify Admin | 5 mins | 🔥 High |
| Immediately verify homepage renders correctly on live site | Human | Browser | 5 mins | 🔥 High |
| Immediately verify /en-us/ market URL is accessible | Human | Browser | 5 mins | 🔥 High |
| Immediately verify doddlbaby.de is still rendering German content correctly | Human | Browser | 5 mins | 🔥 High |
| Immediately run spot check on 5 redirects — confirm no 404s on old URLs | Claude Code | Claude Code | 15 mins | 🔥 High |
| Submit updated sitemap to Google Search Console for doddl.com | Human | Search Console | 10 mins | 🔥 High |
| Submit updated sitemap to Google Search Console for doddlbaby.de | Human | Search Console | 10 mins | 🔥 High |
| Request indexing for all 18 new page URLs via URL Inspection in Search Console | Human | Search Console | 30 mins | 🔥 High |
| Verify GA4 is tracking page views on new page types correctly | Human | GA4 | 20 mins | 🔥 High |

## Post-Launch Monitoring Schedule

| When | What to Check | Owner | Tool |
| --- | --- | --- | --- |
| Day 1–3 | Coverage report — confirm no new 404s or crawl errors | Human | Search Console |
| Day 1–3 | Verify all new pages are being crawled by Googlebot | Human | Search Console → URL Inspection |
| Day 1–3 | Check GA4 data quality — no duplicate purchase events, correct attribution | Human | GA4 |
| Week 1 | Run full redirect spot check — verify all 10 redirects resolving correctly | Claude Code | Claude Code |
| Week 1 | Check hreflang errors in Search Console → Enhancements | Human | Search Console |
| Week 2 | CWV field data check — compare CrUX vs baseline | Claude Code | Claude Code + PSI |
| Week 2 | Rankings check — key product and category terms per market | Human | Search Console |
| Week 4 | Full indexation review — all 18 new pages should be indexed | Human | Search Console |
| Week 4 | doddl.com/en-us/ pages appearing in Google US results | Human | Search Console |
| Week 6–8 | Assess performance stability before starting Phase 2 | Human | Search Console + GA4 |

# Phase 2 — doddlbaby.de Migration (Post-Launch)

⚠ DO NOT start Phase 2 until Phase 1 has been live and stable for at least 4–6 weeks. Running both simultaneously creates unmanageable SEO risk.

Phase 2 migrates Germany from doddlbaby.de to doddl.com/de/. This is a full domain migration and must be treated with the same care as any major URL change.

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| Crawl full doddlbaby.de sitemap — extract every live URL | Claude Code | Claude Code | 1 hr | 🔥 High |
| Build complete 301 redirect map: doddlbaby.de/* → doddl.com/de/* | Claude Code | Claude Code | 2–3 hrs | 🔥 High |
| Activate doddl.com/de/ URL prefix — Admin → Markets → Germany → URL prefix: de | Human | Shopify Admin | 15 mins | 🔥 High |
| Verify German content renders correctly at doddl.com/de/ across all page types | Human + Claude Code | Both | 2 hrs | 🔥 High |
| Implement doddlbaby.de → doddl.com/de/ redirects at domain/hosting level | Human | Domain Host | 1 hr | 🔥 High |
| Update hreflang: change de-DE target from doddlbaby.de → doddl.com/de/ | Claude Code | Claude Code | 30 mins | 🔥 High |
| Update Google Search Console — add doddl.com/de/ as verified property | Human | Search Console | 30 mins | 🔥 High |
| Submit doddl.com/de/ sitemap to Search Console | Human | Search Console | 15 mins | 🔥 High |
| Submit doddlbaby.de Change of Address via Search Console | Human | Search Console | 15 mins | 🔥 High |
| Monitor German organic rankings weekly for 8 weeks post-migration | Human | Search Console | 30 mins/wk | 🔥 High |
| Decommission doddlbaby.de domain once rankings confirmed transferred (minimum 12 weeks) | Human | Domain registrar | 30 mins | ⚡ Medium |

# Post-Launch Workstreams

These items are deliberately excluded from Phase 1 to avoid scope creep. They are confirmed tasks but have their own timelines.

| Task | Owner | Tool | Est. Time | Priority |
| --- | --- | --- | --- | --- |
| GTM and GA4 full audit and reconfiguration — known pain point, separate dedicated session required | Human + Claude Code | Both | TBD | ⚡ Medium |
| Custom event tracking for new page types via Shopify Customer Events | Claude Code | Claude Code | 1 day | ⚡ Medium |
| Full shipping catalog audit and rationalisation across all 10 markets | Human | Shopify Admin | 1 day | 📌 Low |
| French market expansion — translations, market config, content strategy | Human + Claude Code | Both | TBD | 📌 Low |
| doddlbaby.de Phase 2 migration (covered above) | Human + Claude Code | Both | 4–6 wks | 🔥 High |
| Schema audit — full store schema review post-launch including LLM/GEO optimisation | Claude Code | Claude Code | 1 day | ⚡ Medium |
| CWV optimisation sprint — address any regressions identified post-launch | Claude Code | Claude Code | 3–5 days | ⚡ Medium |

# Appendix A — Locked URL Architecture

| Page | URL | Status | Market |
| --- | --- | --- | --- |
| Stage 0 | /collections/weaning-stage-0-6-months | New | All |
| Stage 1 | /collections/baby-cutlery-stage-1-6-12-months | New | All |
| Stage 2 | /collections/toddler-cutlery-stage-2-12-18-months | New | All |
| Stage 3 | /collections/toddler-cutlery-stage-3-18-months-3-years | New | All |
| Stage 4 | /collections/toddler-cutlery-stage-4-3-5-years | New | All |
| Baby cutlery | /collections/baby-cutlery | Rename | All |
| Toddler cutlery | /collections/toddler-cutlery | Rename | All |
| Plates & bowls | /collections/plates-and-bowls | Rename | All |
| Bundles & kits | /collections/bundles-and-kits | Rename | All |
| Bibs | /collections/bibs | New | All |
| SEN hub | /pages/sen-feeding-journey | Evolve | All |
| SEN — Just starting out | /pages/sen-feeding-journey-just-starting-out | New | All |
| SEN — Finding their grip | /pages/sen-feeding-journey-finding-their-grip | New | All |
| SEN — Building confidence | /pages/sen-feeding-journey-building-confidence | New | All |
| SEN — Eating independently | /pages/sen-feeding-journey-eating-independently | New | All |
| Mealtime Dev Box hub | /pages/mealtime-development-box | Evolve | All |
| MDB Stage 1 | /pages/mealtime-development-box-stage-1-6-12-months | New | All |
| MDB Stage 2 | /pages/mealtime-development-box-stage-2-12-18-months | New | All |
| MDB Stage 3 | /pages/mealtime-development-box-stage-3-18-months-3-years | New | All |
| MDB Stage 4 | /pages/mealtime-development-box-stage-4-3-5-years | New | All |
| Research hub | /pages/research-and-development | New | All |

# Appendix B — Issues Log

| # | Issue | Action | Phase | Priority |
| --- | --- | --- | --- | --- |
| 1 | US assigned to Eurozone 1 catalog | Create USD catalog, assign to US market | Phase 0 | 🔥 High |
| 2 | BoostMark inactive but installed | Uninstall BoostMark | Phase 0 | 🔥 High |
| 3 | Shipping catalogs unrationalised | US fix covers immediate need. Full audit post-launch | Post-launch | 📌 Low |
| 4 | doddl.com/de serving live German content | Remove from Germany market domains. Phase 2: migrate to doddl.com/de/ | Both phases | 🔥 High |
| 5 | US market has no indexable URLs | Activate /en-us/ prefix in Markets after catalog fix | Phase 1C | 🔥 High |
| 6 | Hreflang locale codes wrong | Liquid edit — Phase 1 fix + Phase 2 update | Both phases | 🔥 High |
| 7 | shop.doddl.com unknown history | Confirmed redirect to main domain — no action needed | Closed | ✅ Closed |
| 8 | French + Spanish installed but empty | Remove both languages | Phase 0 | 🔥 High |
| 9 | No GTM — native GA4 only | Revisit as dedicated separate workstream | Post-launch | ⚡ Medium |
| 10 | Google Ads not connected | Review connection and feed configuration | Phase 0 | ⚡ Medium |
| 11 | Section Store — unknown page usage | Audit before theme duplication | Phase 1A | 🔥 High |
| 12 | Translate & Adapt — 16 new pages need DE | Translate all new pages before go-live | Phase 1B | 🔥 High |
| 13 | App blocks — Opinew, Tolstoy, Octane, Klarna, Upsell | QA on all affected templates in Phase 1D | Phase 1D | ⚡ Medium |
| 14 | Klaviyo forms on new page templates | Verify renders correctly across all new pages | Phase 1D | ⚡ Medium |